MANUSCRIPT v3 - PUBLICATION CHECKLIST

Senescence Signatures and CAR-T Targets in Systemic Lupus Erythematosus

Working Document | Generated 2026-06-26

Status: GAPS & RESEARCH QUESTIONS IDENTIFIED | READY FOR SYSTEMATIC COMPLETION

# Contents

1. Overview & Completion Roadmap

2. Critical Research Questions (Must Answer Before Writing)

3. SECTION 1: INTRODUCTION (MISSING - ~3-4 pages)

4. SECTION 2: METHODS (PARTIAL - EXPAND)

5. SECTION 3: RESULTS (GOOD - NEEDS REORGANIZATION)

6. SECTION 4: DISCUSSION (MISSING - ~4-5 pages)

7. SECTION 5: FUTURE DIRECTIONS (MISSING - ~1-2 pages)

8. Literature Research Checklist

9. Analysis Checklist

10. Cross-Validation Checklist

# 1. Overview & Completion Roadmap

## Current State

Blueprint v2 = Executive Summary (good for presentations, weak for peer review)

Estimated completion: 4-5 weeks of systematic work

## Work Phases

| Phase | Duration | Output | Gating Criteria |
| --- | --- | --- | --- |
| Research Sprint | 1 week | Answered Q1-Q10, literature review | 15+ papers read, critical gaps identified |
| Methods Writing | 3 days | METHODS.md expanded | All formulas present, choices justified |
| Results Reorganization | 2 days | RESULTS.md separated | Pure findings; no interpretation |
| Discussion Writing | 1 week | DISCUSSION.md created | Literature integrated, mechanisms explained |
| Integration | 3 days | Full manuscript | Sections flow; citations complete |

# 2. Critical Research Questions (Must Answer Before Writing)

These questions block manuscript writing. Answer them via literature search FIRST.

## Q1: SLE EPIDEMIOLOGY: Current prevalence, mortality, standard of care gaps?

Needed for: Introduction - Problem statement

Search Queries:

PubMed: "systemic lupus erythematosus" epidemiology 2023-2024

PubMed: "lupus nephritis" incidence mortality outcomes 2022-2024

Target: Find 3-5 recent epidemiology/outcomes papers

Acceptance Criteria (Question answered when ALL are true):

Global prevalence (millions) with recent citation

Mortality rate and organ involvement statistics

Current standard of care (belimumab, steroids, biologics)

Why current therapies are insufficient

[ ] NOT STARTED

## Q2: CAR-T LANDSCAPE: CD19+ CAR-T successes in SLE? Single-target escape mechanisms?

Needed for: Introduction - Rationale for multi-target approach

Search Queries:

Clinical Trials.gov: CAR-T CD19 SLE lupus (active/closed trials)

PubMed: "CAR-T" "CD19" SLE 2020-2024

PubMed: "CAR-T escape" OR "antigen loss" mechanisms

Target: Find ≥2 SLE CAR-T trials + ≥3 mechanism papers

Acceptance Criteria (Question answered when ALL are true):

Response rates of CD19 CAR-T in SLE trials (if exist)

Alternative: Response rates in B-cell malignancies (proof of concept)

Documented escape mechanisms (CD19-negative relapse)

Rationale for extending beyond CD19

[ ] NOT STARTED

## Q3: SENESCENCE IN AUTOIMMUNITY: How does SLE senescence differ from aging senescence?

Needed for: Introduction - Biological rationale

Search Queries:

PubMed: "senescence" "autoimmune disease" OR "rheumatoid arthritis" 2020-2024

PubMed: "p16" OR "p21" OR "SASP" lupus OR SLE 2019-2024

PubMed: "senescent T cells" OR "senescent B cells" autoimmunity

Target: Find 5+ papers on senescence in autoimmunity

Acceptance Criteria (Question answered when ALL are true):

Evidence that senescence accumulates faster in SLE vs. healthy aging

SASP cytokines (IL-6, TNF, MMP) elevated in SLE

Senescence-driven inflammation in lupus tissues

Prior studies on p16/p21 expression in SLE patients

[ ] NOT STARTED

## Q4: CD38 on senescent cells: Is it a known marker or novel?

Needed for: Discussion - Novelty claim

Search Queries:

PubMed: "CD38" senescent cells OR senescence aging

PubMed: "CD38" "T cells" OR "immune cells" expression

PubMed: "daratumumab" CD38 CAR-T autoimmunity (clinical use)

Target: Determine if CD38 on senescence is established or new

Acceptance Criteria (Question answered when ALL are true):

Prior papers describing CD38 on senescent cells (if exist)

CD38 validation in CAR-T trials (solid tumors, hematologic)

CD38 expression patterns in SLE vs. health

Rationale: Why CD38 is relevant to senescence in SLE

[ ] NOT STARTED

## Q5: CD44 on senescent cells: Known marker or novel?

Needed for: Discussion - Novelty claim

Search Queries:

PubMed: "CD44" senescent cells aging

PubMed: "CD44" "stem cell" OR "memory cells" senescence

PubMed: "CD44" CAR-T trials outcomes toxicity

Target: Determine if CD44 on senescence is established

Acceptance Criteria (Question answered when ALL are true):

Established role of CD44 as memory/stem cell marker

Prior studies: CD44 on senescent cells (if any)

CD44 CAR-T toxicity in preclinical/clinical (endothelium, bone marrow)

Off-target risks explanation

[ ] NOT STARTED

## Q6: CSPG4 on immune cells: Is CSPG4 known on lymphocytes/myeloid cells?

Needed for: Discussion - Critical novelty claim

Search Queries:

PubMed: "CSPG4" immune cells T cells B cells macrophages

PubMed: "CSPG4" senescence

PubMed: "CSPG4" CAR-T trials (not just melanoma)

Target: Determine if CSPG4 on SLE immune cells is novel

Acceptance Criteria (Question answered when ALL are true):

Literature on CSPG4 normal expression (melanoma, stromal cells)

Whether CSPG4 on immune cells is established or NEW

If novel: Strengthen novelty claim; if known: Cite prior work

Validation status in CAR-T trials

[ ] CRITICAL - HIGHEST PRIORITY

## Q7: ICAM1 & VCAM1: Role in lupus pathogenesis?

Needed for: Discussion - Target justification

Search Queries:

PubMed: "ICAM1" OR "VCAM1" lupus OR SLE vasculitis

PubMed: "adhesion molecule" lupus pathogenesis endothelium

PubMed: "ICAM1" CAR-T toxicity (endothelial injury)

Target: Understand why ICAM1/VCAM1 are CAR-T targets

Acceptance Criteria (Question answered when ALL are true):

Elevated ICAM1/VCAM1 in SLE tissues (kidneys, skin)

Role in lupus vasculitis or nephritis pathogenesis

Off-target toxicity: endothelial damage risk

Rationale for including in panel

[ ] NOT STARTED

## Q8: EGFR as CAR-T target: Is EGFR really used in CAR-T or just small molecules?

Needed for: Methods - Target selection

Search Queries:

PubMed: "EGFR" "CAR-T" trials

PubMed: "EGFR" CAR-T cancer (find if it exists)

Target: Validate EGFR as CAR-T target vs. small molecule only

Acceptance Criteria (Question answered when ALL are true):

Published EGFR CAR-T trials (if any)

If no CAR-T trials: Decide whether to drop EGFR

Rationale for including (or excluding) EGFR

[ ] NOT STARTED

## Q9: SenMayo VALIDATION: Has SenMayo been used in other diseases? Validated?

Needed for: Methods - Gene panel justification

Search Queries:

PubMed: "SenMayo" senescence signature (Saul et al. 2022)

PubMed: "SenMayo" applied in [cancer, aging, autoimmunity]

Target: Find 3+ papers citing SenMayo validation

Acceptance Criteria (Question answered when ALL are true):

Saul et al. 2022 Nature Aging paper (primary source)

≥2 independent studies validating SenMayo

Why SenMayo was chosen over alternatives (p16-only, etc.)

Cross-platform applicability demonstrated

[ ] NOT STARTED

## Q10: BATCH CORRECTION: Are Z-score, ComBat, MNN, Seurat compared in literature?

Needed for: Methods - Batch correction justification

Search Queries:

PubMed: "batch correction" "ComBat" vs "mutual nearest neighbors"

PubMed: "Seurat" integration benchmarks across methods

Target: Find 2-3 papers comparing batch correction methods

Acceptance Criteria (Question answered when ALL are true):

Published comparisons of Z-score vs. parametric methods

When each method is appropriate

Why Z-score chosen for 19-dataset meta-analysis

Limitations of Z-score documented

[ ] NOT STARTED

# 3. SECTION 1: INTRODUCTION (MISSING - ~3-4 pages)

Current: None | Needed: Full introduction with literature context

## Subsection 1.1: SLE Epidemiology & Clinical Burden

Current: None | Needed: 1 page

Depends on: Q1

Outline:

Global prevalence (cite: SLE affects ~5 million people)

Mortality rates and organ involvement

Current standard of care limitations (belimumab, steroids)

Why current CAR-T (CD19) is insufficient

[ ] TODO

## Subsection 1.2: Senescence in Aging vs. Autoimmunity

Current: None | Needed: 1 page

Depends on: Q3

Outline:

Define senescence: p16/p21, SASP, telomere shortening

Senescence in healthy aging (slow accumulation)

Senescence in SLE: Accelerated accumulation + inflammatory signature

Why targeting senescence is uniquely relevant to SLE

[ ] TODO

## Subsection 1.3: CAR-T Immunotherapy Landscape

Current: None | Needed: 0.75 page

Depends on: Q2

Outline:

CD19 CAR-T successes in B-cell malignancies (cite JUNO, Kymriah trials)

CD19 CAR-T in SLE (cite trials if exist, else note gap)

Single-target escape mechanisms (antigen loss, downregulation)

Multi-target CAR-T rationale

[ ] TODO

## Subsection 1.4: Existing Senescence Markers & Research Gap

Current: None | Needed: 0.5 page

Depends on: Q4, Q5, Q6

Outline:

Current senescence markers: p16/p21 (nuclear), SASP (soluble)

Lack of surface antigen signatures on senescent cells

Why SenMayo panel is comprehensive (125 genes, 7 pathways)

Gap: No systematic mapping of senescence in SLE

[ ] TODO

## Subsection 1.5: This Study

Current: None | Needed: 0.25 page

Depends on: Q1-Q10

Outline:

Hypothesis: Senescence-associated surface antigens can be identified via multi-dataset analysis

Approach: Apply SenMayo to 19 GEO datasets, identify surface antigens

Innovation: Multi-target CAR-T targets identified computationally

Outcome: 6 candidate targets for experimental validation

[ ] TODO

# 4. SECTION 2: METHODS (PARTIAL - EXPAND)

Current: docs/METHODS.md exists but needs formula detail & justifications

## Methods 2.1: Dataset Selection Criteria (NEEDS CLARIFICATION)

Current: 7 inclusion / 5 exclusion criteria listed

Gap: Need to explain: Why no SLEDAI? Why datasets with n=2 patients?

Action: Add subsection: "Limitations of GEO metadata (0 datasets have SLEDAI; why we proceeded)"

Depends on: Q1

[ ] TODO

## Methods 2.2: Batch Correction Method Choice (NEEDS JUSTIFICATION)

Current: Z-score described, but comparison missing

Gap: Need to compare: Z-score vs. ComBat vs. MNN vs. Seurat. Why NOT others?

Action: Add table comparing 4 methods + justification for Z-score choice

Depends on: Q10

[ ] TODO

## Methods 2.3: Senescence Scoring Algorithm (NEEDS MATH)

Current: Verbal description present

Gap: Need exact formulas for Z-score, fallback logic, global re-centering

Action: Add: Mathematical formulas for S_raw, S_z, S_corrected + pseudocode

Depends on: Q9

[ ] TODO

## Methods 2.4: Statistical Testing Details (NEEDS SPECIFICS)

Current: Tests listed (Kruskal-Wallis, Bonferroni mentioned)

Gap: Need: Exact implementation details, why non-parametric, post-hoc tests

Action: Add: Alpha levels, Bonferroni formula as implemented, normality tests if any

[ ] TODO

## Methods 2.5: CAR-T Target Selection (NEEDS LITERATURE)

Current: 6 targets listed with brief criteria

Gap: Need: Why these 6? Literature support for each? Why NOT others?

Action: Add: Table with clinical status of each target + citations

Depends on: Q4, Q5, Q6, Q7, Q8

[ ] TODO

# 5. SECTION 3: RESULTS (GOOD - NEEDS REORGANIZATION)

Current: docs/RESULTS.md has good data but conflates findings with interpretation

## Results 3.1: Remove Interpretation, Keep Pure Findings

Current: "CD38, CD44 show consistent correlation with senescence"

Needed: "Spearman r=0.40 (p=0.007), r=0.36 (p=0.017) in GSE228066 (n=45)"

[ ] TODO

## Results 3.2: Add Target Correlation Heatmap & Independence Matrix

Current: Separate correlations reported

Needed: Compute: Correlation between CD38 and CD44 expression (are they independent?)

Action: Run analysis: Correlation matrix for 6 targets in 3 datasets

[ ] TODO

## Results 3.3: Explain Cross-Tissue Heterogeneity (Kidney > Synovium)

Current: Variance reported but not explained

Needed: Why kidney shows senescence, synovium does not? Defer to Discussion.

Action: Move interpretation to Discussion; Results = numbers only

[ ] TODO

## Results 3.4: Separate Results from Discussion

Current: Findings mixed with "suggests," "indicates," "validates"

Needed: Results: data only. Discussion: interpretation

Action: Rewrite RESULTS.md as pure findings; create DISCUSSION.md for interpretation

[ ] TODO

# 6. SECTION 4: DISCUSSION (MISSING - ~4-5 pages)

Current: None | Needed: Full discussion integrating literature

## Subsection 4.1: Comparison to Existing SLE Therapies

Length: 1 page

Key Points:

Belimumab (B-cell activator inhibitor): Response rates, long-term outcomes

CD19 CAR-T: Response rates, flare prevention, toxicity

Proposed: Senescence-targeting CAR-T as complement or alternative

Rationale: Why targeting senescence + CD19 may be superior to CD19 alone

Depends on: Q1, Q2

[ ] TODO

## Subsection 4.2: Interpretation of Multi-Target > Single-Target

Length: 0.75 page

Key Points:

Data: Combined CD38+CD44+CSPG4 (r=0.576) > individuals (r=0.23-0.40)

Question: Are targets additive (different cells) or redundant (same cell)?

Analysis needed: Compute correlation matrix (do targets correlate?)

Mechanistic explanation: Why combination outperforms singles

Depends on: Results 3.2

[ ] TODO

## Subsection 4.3: Off-Target Toxicity Risk Analysis

Length: 0.75 page

Key Points:

CD38: Normal expression on plasma cells, T cells, NK cells

CD44: Hematopoietic stem cells, memory T cells, endothelium

CSPG4: [Based on literature answer to Q6]

ICAM1: Endothelium (vascular injury risk)

VCAM1: Endothelium, immune cells

Prior CAR-T toxicities: Summarize from clinical trials

Mitigation: Patient selection, combination with senolytics

Depends on: Q4, Q5, Q6, Q7

[ ] TODO

## Subsection 4.4: Novelty of Each Target

Length: 1 page

Key Points:

CD38: "Validated in CAR-T trials [CITE]; our contribution is validating in SLE senescence context"

CD44: "Known memory marker; novel as senescence-associated surface antigen"

CSPG4: "[Based on Q6 answer] If novel on immune cells: strong claim; if known: position as validation"

ICAM1/VCAM1: "Endothelial markers in lupus; novel association with senescence"

Overall novelty: "First comprehensive senescence-surface antigen mapping in SLE"

Depends on: Q4, Q5, Q6

[ ] TODO

## Subsection 4.5: Tissue-Specific Senescence Patterns

Length: 0.75 page

Key Points:

Observation: Kidney senescence > synovium senescence

Hypothesis: Different pathogenic mechanisms (humoral vs. cellular immunity)

Literature: Lupus nephritis = antibody-driven; arthritis = mixed

Implication: Senescence-targeting CAR-T may be kidney-preferential benefit

Future: Tissue-specific senescence scoring in larger cohorts

Depends on:

[ ] TODO

## Subsection 4.6: Limitations & Caveats

Length: 0.5 page

Key Points:

No SLEDAI metadata: Cannot measure senescence-activity correlation

Fallback scoring: 15/19 datasets use variable genes, not SenMayo directly

No functional validation: Computational discovery only; wet-lab validation required

CD44/ICAM1 broad expression: Off-target toxicity risks

Small sample sizes: Some datasets (n=2-3 patients)

Depends on:

[ ] TODO

# 7. SECTION 5: FUTURE DIRECTIONS (MISSING - ~1-2 pages)

Current: Implicit in Limitations | Needed: Explicit 3-tier roadmap

## Subsection 5.1: Computational Validation (Immediate - 3-6 months)

[ ] Ensembl-to-HUGO mapping for 15 fallback datasets

[ ] Sensitivity analysis: Score robustness to gene selection (top 13 vs. top 20)

[ ] Cross-validation: Apply SenMayo to independent SLE RNA-seq (GEO search)

[ ] Benchmark: GSVA/ssGSEA vs. mean expression scoring

## Subsection 5.2: In Vitro Validation (6-12 months)

[ ] Flow cytometry: CD38/CD44/CSPG4 on senescent vs. non-senescent SLE PBMCs (n=10 active, 10 inactive)

[ ] Co-culture killing: CAR-T efficacy against senescent cells (each target separately)

[ ] SASP measurement: IL-6, TNF-α reduction after senescent cell clearance

[ ] CSPG4 validation: Immunofluorescence on patient samples (confirm immune cell expression)

## Subsection 5.3: In Vivo Validation (12-24 months)

[ ] Senescence burden: Quantify p16/p21 in lupus-prone mice (MRL/lpr, NZB/W)

[ ] CAR-T efficacy: Multi-target vs. single-target in murine SLE

[ ] Safety profile: Off-target toxicity (bone marrow, endothelium)

[ ] Optimal targets: Which 1-3 targets show best efficacy/safety profile?

## Subsection 5.4: Clinical Translation (24+ months)

Patient selection criteria: High senescence burden (>median score)

Combination strategies: CAR-T + senolytics (fisetin, quercetin)?

Timing optimization: Early vs. late disease (when is senescence burden highest?)

Flare prevention: Does senescence-targeting CAR-T reduce flare rate?

# 8. Literature Research Checklist

Track progress of PubMed/Clinical Trials searches for each question

| Question | Searches Completed | Papers Found | Key Findings |
| --- | --- | --- | --- |
| Q1 | [ ] NOT STARTED | 0 | [pending] |
| Q2 | [ ] NOT STARTED | 0 | [pending] |
| Q3 | [ ] NOT STARTED | 0 | [pending] |
| Q4 | [ ] NOT STARTED | 0 | [pending] |
| Q5 | [ ] NOT STARTED | 0 | [pending] |
| Q6 | [ ] NOT STARTED | 0 | [pending] |
| Q7 | [ ] NOT STARTED | 0 | [pending] |
| Q8 | [ ] NOT STARTED | 0 | [pending] |
| Q9 | [ ] NOT STARTED | 0 | [pending] |
| Q10 | [ ] NOT STARTED | 0 | [pending] |

# 9. Analysis Checklist

Track completion of computational analyses needed for manuscript

Compute target correlation matrix (6 targets, 3 datasets) [ ] TODO

Determine if targets are independent (Pearson r < 0.5?) or redundant [ ] TODO

Verify Bonferroni correction is implemented correctly in code [ ] TODO

Check: Are results reproducible if pipeline re-run? [ ] TODO

Quantify: How many genes matched SenMayo per dataset? (should be in table) [ ] TODO

Verify: All 19 datasets have senescence scores in external_validation/ [ ] TODO

# 10. Cross-Validation Checklist

Ensure consistency across all sections

All numbers match across sections (19 datasets, 2,919 samples, 125 genes) [ ] TODO

All citations formatted consistently (Author YYYY) [ ] TODO

No conflation of Results and Discussion [ ] TODO

Methods justify all choices (batch correction, targets, statistics) [ ] TODO

Introduction flows to Methods flows to Results flows to Discussion [ ] TODO

Future Directions are ambitious but achievable with resources listed [ ] TODO

No overselling ("first," "revolutionary") without literature support [ ] TODO

# How to Use This Checklist

1. PHASE 1 (Week 1): Complete all Q1-Q10 literature research. Update status from [NOT STARTED] to [COMPLETE].

2. PHASE 2 (Week 2-3): Expand METHODS.md with all formulas, justifications, table comparisons.

3. PHASE 3 (Week 3): Reorganize RESULTS.md: pure findings only (no interpretation).

4. PHASE 4 (Week 4): Write DISCUSSION.md with literature integration.

5. PHASE 5 (Week 5): Write FUTURE_DIRECTIONS.md with 3-tier roadmap.

6. INTEGRATION: Merge all sections into single manuscript (Word/LaTeX).

7. VALIDATION: Complete all cross-validation checklists.

8. FINAL: Proofread, check citations, verify numbers match throughout.

Target completion: 5 weeks of systematic work

Blocker: Cannot write until Q1-Q10 are answered